# Time Tracking

# Medsov Telehealth Time Tracking

Tracking basis: 1 development day = 8 hours.

Current workbook: docs/medsov-telehealth-time-tracking-interview.xlsx

Current status: 192 human-equivalent hours logged across the two-week project window, 100% complete against the current stated module requirements. Packaging/install validation, OpenEMR 8 Patch-3 compatibility validation, security review, fresh regression testing, performance timing, recovery validation, participant limit enforcement, encounter association, and final handoff documentation are complete.

## Completed Since Last Report

| Date | Task | Estimate | Actual | Variance | Status | Notes |
| --- | --- | --- | --- | --- | --- | --- |
| 2026-06-15 | Admin configuration page and feature flags | 8 hrs | 8 hrs | 0 hrs | Done | Added Medsov-branded setup page for module enablement, waiting room, audio/video, email/SMS flags, Jitsi settings, and participant capacity. |
| 2026-06-15 | Telehealth audit log UI | 12 hrs | 12 hrs | 0 hrs | Done | Added Admin -> Medsov Telehealth -> Audit Log with event, actor, status, date, patient, provider, session, and appointment filters. |
| 2026-06-16 | Final install and release packaging | 10 hrs | 10 hrs | 0 hrs | Done | Added release zip builder, install validator, package README, and validated safe table.sql rerun in Docker. |
| 2026-06-16 | Formal test evidence report | 12 hrs | 12 hrs | 0 hrs | Done | Ran automated/service-level checks for core required flows, including true Doctor A/Doctor B cross-provider access control, and created docs/test-evidence-report.docx. |
| 2026-06-16 | OpenEMR 8 Patch-3 compatibility validation | 4 hrs | 4 hrs | 0 hrs | Done | Upgraded the main Docker stack to openemr/openemr:8.0.0.3 and validated module install/package behavior on port 8080. |
| 2026-06-17 | Final security review and regression rerun | Included | Included | 0 hrs | Done | Confirmed provider access control, patient ownership/token checks, cancelled appointment blocking, direct URL rejection, CSRF rejection, and Patch 3 regression results. |
| 2026-06-17 | Final interviewer handoff documentation | Included | Included | 0 hrs | Done | Added docs/final-interviewer-handoff.docx and refreshed docs/test-evidence-report.docx. |
| 2026-06-18 | Provider upcoming telehealth appointments | Included | Included | 0 hrs | Done | Added provider/admin upcoming appointments page with Start/Open Appointment actions and browser regression coverage. |
| 2026-06-18 | Reliability and performance validation | Included | Included | 0 hrs | Done | Added recovery check plus timed performance script for meeting launch, provider queue, email, and floating alert thresholds. |
| 2026-06-18 | Expanded installation/configuration/deployment/user docs | Included | Included | 0 hrs | Done | Added dedicated guides and clarified SMS is not in scope for this build. |
| 2026-06-18 | Clean Module Manager install validation | Included | Included | 0 hrs | Done | Rebuilt the zip with Linux-safe paths and validated clean OpenEMR Patch 3 Module Manager activation outside the bind-mounted development workflow. |
| 2026-06-18 | Encounter association | Included | Included | 0 hrs | Done | Linked provider-launched telehealth sessions to OpenEMR form_encounter and forms records, stored the encounter number on the telehealth session, and added audit evidence. |
| 2026-06-18 | Participant limit enforcement | Included | Included | 0 hrs | Done | Enforced configured participant capacity before Jitsi launch, added participant heartbeat/leave tracking, and validated limit rejection/audit behavior. |
| 2026-06-19 | Final GitHub submission preparation | Included | Included | 0 hrs | Done | Cleaned local-only files, ignored secrets/runtime artifacts, kept final installable package, and prepared the repository for interviewer review. |

## Current Completed Scope

| Workstream | Status | Notes |
| --- | --- | --- |
| Docker/OpenEMR environment | Done | OpenEMR, MariaDB, mounted module workflow, and Mailpit SMTP testing are working. |
| Module architecture | Done | Modern OpenEMR module structure, bootstrap, metadata, service layer, templates, and SQL are in place. |
| Provider appointment integration | Done | Medsov Telehealth appointments show Start Telehealth, Open Full Screen, Copy Room, and Admit Patient controls. |
| Encounter association | Done | Provider launch creates or reuses a linked OpenEMR encounter and stores it on the telehealth session. |
| Provider upcoming appointments | Done | Provider/admin list shows upcoming Medsov Telehealth appointments with status, Start, and Open Appointment actions. |
| Embedded Jitsi integration | Done | Public meet.jit.si is embedded inside OpenEMR and Patient Portal pages. |
| Participant limit enforcement | Done | Configured max participant count is enforced before provider/patient Jitsi entry; stale participants expire and leave frees capacity. |
| Patient Portal integration | Done | Patients can view upcoming telehealth visits, check devices, enter waiting room, and join after admission. |
| Waiting room and admission | Done | Patient waiting state, provider alert, admit workflow, and waiting-room polling are implemented. |
| Notifications | Done | Provider UI alert, provider email, OpenEMR Message Center notification, patient invite/update/provider-started/cancellation emails are implemented. |
| Security/access control | Done | Assigned provider can manage assigned visits, admin can manage all, and patient can access only their own visit. |
| Cancellation workflow | Done | Cancelled telehealth appointments cancel the session, email the patient, hide from portal join list, and write audit events. |
| Audit logging | Done | Backend audit events and admin audit log UI are implemented. |
| Testing | Done | Formal test evidence report covers core flows, package validation, cancellation, audit storage, true Doctor A/Doctor B access control, performance, and recovery. |
| Packaging/install validation | Done | Final release zip is generated in dist/, package contents were checked, clean Module Manager activation passed, and install SQL validation passed on OpenEMR 8.0.0 and OpenEMR 8 Patch 3. |
| Final handoff documentation | Done | Interview-facing Markdown and DOCX handoff documents are available in docs/. |

## Remaining Follow-Up Items

| Item | Estimate | Priority | Notes |
| --- | --- | --- | --- |
| Production SMTP configuration | Environment dependent | External | Local Mailpit testing is complete; real SMTP credentials/domains must be supplied by deployment environment. |
| Production/private Jitsi configuration | Environment dependent | External | Public meet.jit.si testing is complete; production domain can be configured in the admin page. |
| Scheduled reminder emails | 10 hrs | Optional | Only build if the interviewer explicitly confirms pre-visit reminder emails are required. |

## Progress Report Template

Date:

Completed tasks:

Time spent:

Remaining estimate:

Risks/blockers:

Percent complete:

Next tasks: